## Sheet1
PHASE 1
Sl No. | Points | Difficulty | Details | Status
Maps
1 | We do not need routes on the map rather we would like the use of static patrol points | easy | We can use several static markers at every time interval to show the position of the vehicle | Done
2 | For a PRV each static point should have a separate colour | easy | Different Image files can be used to show different icons. But high number of vechicles can be an issue. | Pending
3 | Please add labels so that we can related the time slots for a PRV with provided excel Label should have this information: I. Vehicle Id II. Time Slot | moderate | We can use Popup at every marker to show this information | Done
Excel Data
4 | We believe column B represent PRV ID and column A represent time slots. But the values in columns are not available for all 24 slots rather they are for 20 and at times 19 slots, request you please have a look at same | easy | This is due to (total number of steps per iteration)/(number of vechicle). Can be adjusted to show 24 locations. | Done
Multiple Views
Current view is appealing but it would be of more practical use if we have 2 separate views:
5 | i. PRVView (Individual vehicle view):This view will be represented by dots and each dot should have time label, with aforementioned specifications | difficult | There is a function which handles onclick event on every maker. We can have a separate view for each vehicle onclick of the marker. But, as the library is new. There is no proper implemenatation example. | Work in Progress
6 | ii. Fleet View (All vehicle view): This view will have filter control based on time slots and dates | difficult | This is our default view. We need to add filter to the view. | Work in Progress
Extra Tasks
7 | Connecting Q-learning algorithm output to database | Moderate | To directly update the routes to the database | Done
8 | Deploying the project to the IITK server | Moderate | Deployment | Pending